## Sheet1
Project Title : |  | Assessment Project - Number Collector
Start Date : |  | 2023-11-02 |  |  | End Date : |  | 2023-11-07 |  |  | Duration : |  | 5 |  |  | Present Date : |  | 2023-11-09
WBS No | Tasks Name |  |  |  |  | 2023-11-02 |  | 2023-11-03 | 2023-11-04 |  | 2023-11-05 |  | 2023-11-06 | 2023-11-07 |  | 2023-11-08 |  | 2023-11-09
1 | Planing |  |  |  |  | StartDate | [8 empty] | EndDate |  |  | Presentation
2
2 | Developement |  | Frontend | Home |  |  |  | 3
|  |  |  | 404 |  |  |  | 1
|  |  |  | Records | [7 empty] | 2
|  |  |  | - Components |  |  |  |  | 3
|  |  | Backend | Database | [7 empty] | 2
|  |  |  | Connect Database | [7 empty] | 2
|  |  |  | Create Record | [7 empty] | 2
|  |  |  | Get Records | [7 empty] | 2
| Testing & Debug | [8 empty] | 3
| Information Prepare | [5 empty] | 5